## Milestone 1
Team Name |  |  | Team Plus Plus
Member name 1 |  |  | Noel Ortiz
Member name 2 |  |  | Matthew Phillips
Member name 3 |  |  | Brandon Vergara
Member name 4 |  |  | Ryan Reed
Milestone 1 rubric | 2 person team | 3 person team | 4 person team
Task Name | Point Value | Point Value | Point Value | Details - Infomration that will show the work will be demonstable, to a new commer
Required Tasks |  |  |  | These tasks must be completed
Rendering Basic | 15 | 10 | 7 | Display a ground plane | M
Rendering Bind Pose | 15 | 11 | 7 | Draw all the bones (as spheres) in thier world positions (this task is blocked until FBX exporter gets the information) | B
Rendering Model | 20 | 14 | 10 | Draw the animated box model (In Course content/Test Assets) from an FBX file, textured in bind pose using the correct math (this task is blocked until FBX exporter gets the information) | N
Rendering Lights | 5 | 5 | 5 | Render a type of dynamic light (select Directional, Point or Spot Light). The correct light is applied to the model at all angles | R
Render List |  | 10 | 6 | Create a render Node that can be stored in a container. The render function should use a loop to deal with each type of render node (Nodes requried are animated and static and the ability to change from fill mode to wireframe) | R\M
Export FBX data | 15 | 13 | 9 | In a seprate project, in the same solution, create a DLL. This project will get all the information from the the FBX file. The exe file must use this DLL to read the FBX file. | N
No issues | 5 | 5 | 5 | No warnings, crashes, application verifier stops or memory leaks | E
Flexible Tasks |  |  |  | Tasks that will make your project your own
Controlable camera | 15 | 12 | 8 | Use keyboard for movement and mouse for rotation of the camera (This is an example of a flexible task, and can be changed. It is recommended to stay as it will make de bugging easier. This task can get moved forward, if not finished) | B
Instancing |  |  | 11 |  | M
Transparency |  |  | 11 | Transparent shader for making models see through. | R
|  |  | 11 |  | N
|  |  | 10 |  | B
Total | 90 | 80 | 100 | Must equal 100
Note on E12: This task cannot get moved forward. In order to complete the task from milestone 2 called, Render Each Key frame, the bind pose has to be working.
Note on B14: This can be selected for a two man team but this is not required for teams of this size. This task will not be applied to tasks needed to still be working on the next milestones for teams for 2 as well.

## Milestone 2
Team Name
Member name 1
Member name 2
Member name 3
Milestone 1 rubric | 2 person team | 3 person team
Task Name | Point Value | Point Value | Details - Infomration that will show the work will be demonstable, to a new commer
Required Tasks |  |  | These tasks must be completed
Render Each Key frame | 30 | 26 | Based on a key press, show each frame of an animation (with bones and mesh)
Loop Animation | 10 | 10 | Show an animation looping without a key press with proper interpolation (not linear)
Switch Model | 20 | 14 | Be able to show both the bear and the animed box models, with bones from the FBX file (Can recompile for the switch)
Binary Loading and exporting | 15 | 15 | The FBX project should create a binary file that the main project reads. There cannot be any knowledge of FBXSDK.h in the main project
Features added | 10 | 10 | All tasks from the previous milestone (All required tasks and completed flexible tasks) still work and can be deomstronstated in this milestone.
No issues | 5 | 5 | No warnings, crashes, application verifier stops or memory leaks
Flexible Tasks |  |  | Tasks that will make your project your own
Total | 90 | 80 | Must equal 100
Note on D9: This task cannot get moved forward. The task, Blended Animations, from next milestone, will need this task to be working to complete that task.
Note on D10: This task cannot get moved forward. The task, Blended Animations, from next milestone, will need this task to be working to complete that task.

## Milestone 3
Team Name
Member name 1
Member name 2
Member name 3
Milestone 1 rubric | 2 person team | 3 person team
Task Name | Point Value | Point Value | Details - Infomration that will show the work will be demonstable, to a new commer
Required Tasks |  |  | These tasks must be completed
Skinned Animation | 15 | 12 | The animation math must be on the GPU
Blended Animations | 30 | 25 | On a key press, be able to go from one animation to another without a pop (example idle to run)
Switch Model | 10 | 7 | Show the Mage, the bear and the animed box models, with bones (in world space) from a binary file. It is acceptable to recomile to switch meshs. It is also acceptable to load up from the FBX to create a binary file on the first run only, but subsequest runs load the binary file.
Rendering | 20 | 15 | Use the diffuse, specular and normal map textures of the mage and show lighting working correctly
Features added | 10 | 10 | All tasks from the previous two milestones (All required tasks and completed flexible tasks) still work and can be deomstronstated in this milestone.
No issues | 5 | 5 | No warnings, crashes, application verifier stops or memory leaks
Flexible Tasks |  |  | Tasks that will make your project your own
Total | 90 | 74 | Must equal 100